# Table 2.2 Elements of an ID PM Plan

| Element | Description |
| --- | --- |
| Team Formation | Decide who should be on the team and the roles and responsibilities of each. |
| Stakeholders | State the details of the stakeholders. |
| Target Audience & Goals | Describe the intended learners and goals of the education or training. |
| Scope | Define what the ID project contains, summarizing all the work required to successfully complete the instruction. |
| References | Identify all necessary policies, guidance, and directives applicable to the instruction. |
| Constraints & Assumptions | Identify all known or potential problems or issues and assumptions that could arise during the ID process (e.g., resources, labor, security, safety, environmental issues). |
| Project management strategies | Determine the way the team will work (decision-making process, frequency of meetings to discuss project progress, methods of communication and reporting, etc.) |
| Definition and Sequence of ID Activities | Determine specific activities and interactivity dependencies that must be performed to produce various project deliverables. |
| Timeline and Resources | Create an ID project timeline identifying activity sequences, durations, and resource requirements. |
| Estimated Costs | Determine an approximation of (1) the costs for the ID process and (2) the costs of implementing instruction (resources, people, equipment, infrastructure). |
| Budget | Establish a cost baseline for allocated funds and resources for the ID process and for implementing the instruction. |
| ID Process Evaluation | Develop an evaluation plan to improve process quality throughout the ID process (see below for more details). |
| Other Considerations | Produce written plans that detail how to execute, monitor, and control each of the activities of the ID process: analysis/design, development, implementation, and evaluation. Plan for the ID project closing processes, during which the project manager evaluates and documents all project activities to capture the lessons learned and finalize the project. Consider the effects of the ID project on the client’s organization. |